## Sheet1
Sprint 3 Backlog -- Product owner:wennad
Time | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25
Yunpeng | Task1: Filter & category |  |  | Scrum meeting & Integration
Yulun | Task2: Dynamic Search, get more diverse data
Wenna | Task3: Add user's favorite dish recipes, google map feature according to user's input
Time | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03
Yunpeng | Task4: improve shopping list, price display, email |  |  |  |  | Scrum meeting & Integration | Task 7: Integration test and debug
Yulun | Task5: shopping list print, user history record and recommend
Wenna | Task6: Recommendation page features, random and filter
Task | Priority | Status | Cost (hours) | Sub tasks |  | Sub cost (hours) | Sub status
1 | High | Not started | 16 | Filter & category |  | 16 | Not started
2 | High | Not started | 20 | Dynamic search |  | 16 | Not started
|  |  |  | Get more diverse data |  | 4 | Not started
3 | low | Not started | 16 | User's favorite dish recipes |  | 8 | Not started
|  |  |  | Google map input |  | 8 | Not started
4 | Medium | Not started | 20 | improve shopping list |  | 12 | completed
|  |  |  | price display, email |  | 8 | Not started
5 | Medium | Not started | 20 | shopping list print, user history record and recommend |  | 20 | Not started
6 | High | Not started | 24 | Recommendation page UI |  | 14 | Not started
|  |  |  | Random and filter feature |  | 10 | Not started
7 | High | Not started | 24 | Testing and debugging |  | 24 | Not started