## Sheet1
Sprint 1 Backlog -- Product owner: yulunt
Time | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06
Yunpeng | Task1: base.html & css & main page |  |  |  | Task4: profile + comments |  |  |  |  | Task7: Integration + Presentation preparation
Yulun | Task2: Scrapy/ beautiful soup/ youtube API |  |  |  | Task5: Recommendation page + shopping list
Wenna | Task3: HTML Geolocation & Google map API |  |  |  | Task6: dish page + google map
Task | Priority | Status | Cost | Sub tasks | Sub cost | Sub status
1 | High | Not started | 12 hours | base page layout | 4 | Not started
|  |  |  | base page css | 4 | Not started
|  |  |  | main page layout | 4 | Not started
2 | Medium | Not started | 10 hours | embed video in html | 2 | Not started
|  |  |  | scrapy tutorial and example | 3 | Not started
|  |  |  | beautiful soup tutorial and example | 3 | Not started
|  |  |  | Tutorial note | 2 | Not started
3 | Low | Not started | 10 hours | Survey | 3 | Not started
|  |  |  | Tutorial and example | 5 | Not started
|  |  |  | Tutorial note | 2 | Not started
4 | Medium | Not started | 8 hours | profile page layout | 4 | Not started
|  |  |  | comments page layout | 4 | Not started
5 | Medium | Not started | 8 hours | Recommendation | 4 | Not started
|  |  |  | shopping list | 4 | Not started
6 | Medium | Not started | 8 hours | dish.html | 3 | Not started
|  |  |  | dish.css | 3 | Not started
|  |  |  | google map | 2 | Not started
7 | Low | Not started | 5*3 hours | Integration + presentation preparation | 5 | Not started