## Sheet1
Sprint 2 Backlog -- Product owner:yunpengx
Time | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11
Yunpeng | Task1: study React.js |  |  | Scrum meeting & Integration
Yulun | Task2: Revise youtube size, parser to extract units of ingredient and complete unit conversion
Wenna | Task3: learn FB login api Oauth
Time | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21
Yunpeng | Task4: loading more recipes, price information display |  |  |  |  | Scrum meeting & Integration | Task7: image preprocessing with js |  | Scrum meeting & Integration | Presentation prepation
Yulun | Task5: crawler to gather price information of ingredient | [5 empty] | Task8: SSL issue with google map
Wenna | Task6: Django navigation and database interaction | [5 empty] | Task9: Revise UI on all platforms
Task | Priority | Status | Cost (hours) | Sub tasks |  | Sub cost (hours) | Sub status
1 | Medium | Not started | 20 | use React.js with Django |  | 4 | started
|  |  |  | basic usage and demo code |  | 16 | completed
2 | High | Not started | 20 | Django model modification |  | 2 | Not started
|  |  |  | Beautifulsoup web crawler to get data |  | 8 | Not started
|  |  |  | python parser for ingredient price information |  | 9 | Not started
|  |  |  | Youtube resize |  | 1 | completed
3 | Medium | Not started | 16 | Oauth API study |  | 8 | Not started
|  |  |  | Implement Oauth login |  | 8 | Not started
4 | Medium | Not started | 16 | loading more recipes |  | 8 | started
|  |  |  | price information display |  | 8 | Not started
5 | High | Not started | 8 | crawler to gather price information of ingredient |  | 4 | Not started
6 | High | Not started | 16 | Django navigation |  | 4 | Not started
|  |  |  | Database interaction |  | 4 | Not started
7 | Low | Not started | 4 | image preprocessing with js |  | 4 | completed
8 | Low | Not started | 4 | issue with google map |  | 4 | Not started
9 | Medium | Not started | 4 | Revise UI on all platforms |  | 4 | Not started